## Slide 1
TechCorp IAM Platform
Implementation Plan
A Secure, Scalable Identity & Access Management Roadmap
Prepared by: Prince Ndutimi | TechCorp Security Team | Confidential

## Slide 2
Objectives & Business Alignment
BUSINESS GOALS
Strengthen overall cybersecurity posture and reduce attack surface
Streamline user access provisioning and de-provisioning workflows
Ensure regulatory compliance (GDPR, SOX, ISO 27001)
Establish a zero-trust identity framework across all systems
Reduce insider threat risk through least-privilege enforcement
IAM BENEFITS
Significant reduction in unauthorised access and data breach risk
Faster employee onboarding and offboarding cycles
Improved operational efficiency through automated provisioning
Centralised visibility and audit trail for all access events
Scalable architecture supporting future cloud expansion

## Slide 3
Implementation Phases & Timeline
Phase 1
Planning &
Assessment
Month 1–2
Phase 2
Design &
Architecture
Month 3
Phase 3
Pilot
Testing
Month 4
Phase 4
Deployment
& Cutover
Month 5–6
Phase 5
Training &
Go-Live
Month 7
Phase 6
Monitoring &
Optimisation
Ongoing
Total estimated implementation duration: 7 months with ongoing monitoring

## Slide 4
Phase 1 — Planning & Assessment | Month 1–2
KEY TASKS
Conduct full inventory of existing systems, users, roles, and access rights
Identify and classify all privileged accounts and sensitive resources
Define IAM policies including RBAC and ABAC frameworks
Conduct stakeholder workshops with IT, HR, Compliance, and Business units
Perform gap analysis between current access controls and target IAM state
Document all integration points and legacy system dependencies
RESOURCES
IAM Programme Lead
Security Architect
Compliance Officers
HR Systems Admin
Legacy System SMEs
Business Unit Leads

## Slide 5
Phase 2 — Design & Architecture | Month 3
Core IAM Components
Single Sign-On (SSO) across all applications
Multi-Factor Authentication (MFA) enforcement
Privileged Access Management (PAM)
Role-Based Access Control (RBAC)
Attribute-Based Access Control (ABAC)
Architecture Model
Hybrid cloud + on-premises architecture
Federated identity across business units
Zero-trust perimeter enforcement
API gateway integration for all apps
Centralised identity store with sync agents
Platform & Tools
Okta or Microsoft Azure Active Directory
SailPoint for identity governance
CyberArk for privileged access management
SAML 2.0 and OAuth 2.0 protocols
Active Directory Federation Services (ADFS)

## Slide 6
Integration Challenges & Solutions
Challenge
Solution
Risk
Legacy system APIs incompatible with modern IAM protocols
Develop custom connectors and middleware adapters for each legacy system
Medium
Cloud application compatibility with on-premises identity store
Implement SAML 2.0 and OAuth 2.0 federation protocols as standard integration layer
Low
Data consistency across distributed identity repositories
Deploy real-time identity sync engines with conflict resolution logic
Medium
User resistance and productivity disruption during cutover
Phased rollout with parallel operation period and dedicated helpdesk support
Low

## Slide 7
Phase 3 — Pilot Testing | Month 4
PILOT SCOPE
Target group: IT department (25 users) as pilot cohort
Test critical workflows: employee onboarding and offboarding
Validate SSO across the 5 most-used enterprise applications
Test MFA rollout and user enrolment experience end-to-end
Simulate access request, approval, and revocation workflows
Stress test PAM controls for privileged account management
Document all defects, edge cases, and user experience issues
SUCCESS METRICS
< 5%
Error rate across all test workflows
< 30 min
Access provisioning turnaround time
> 95%
SSO authentication success rate
100%
MFA enrolment completion for pilot users

## Slide 8
Phase 4 — Deployment & Cutover | Month 5–6
PHASED ROLLOUT STRATEGY
Wave 1
IT Department
Week 1–2
Wave 2
Finance
Week 3–4
Wave 3
HR & Operations
Week 5–6
Wave 4
All Remaining
Departments
Week 7–8
FALLBACK & CONTINGENCY PLAN
Pre-cutover rollback snapshots maintained for all legacy identity systems
Automated health checks trigger rollback if error rates exceed 5% threshold
Dedicated cutover war room with IT leads, security team, and executive sponsor
24/7 helpdesk support enabled during the first two weeks post-deployment

## Slide 9
Training & Change Management | Month 7
End-User Training
Self-service video tutorial library covering SSO and MFA enrolment
Interactive FAQ portal with searchable knowledge base
Department-specific quick-start guides distributed pre-launch
Live Q&A drop-in sessions during the first two weeks
Email campaign: phased communications leading up to go-live
Administrator Training
Hands-on lab environment replicating production IAM platform
Policy enforcement and RBAC administration workshops
Incident response playbooks for IAM-related security events
SailPoint and Okta/Azure AD administration certification path
Monthly admin refresher sessions post go-live
Change Management
Executive sponsor visible and active throughout programme
Departmental IAM champions identified in each business unit
Feedback loops established via surveys after each wave
Resistance escalation path defined and communicated clearly
Success stories shared internally to build programme confidence

## Slide 10
Monitoring & Continuous Improvement | Ongoing
MONITORING TOOLS & INTEGRATIONS
SIEM integration for real-time alert correlation and IAM event logging
Anomaly detection engine for unusual access patterns and login behaviour
Automated access review scheduler (quarterly for standard users, monthly for privileged)
User behaviour analytics (UBA) to detect compromised accounts
Privileged session recording and audit logging via PAM platform
Executive dashboard with real-time IAM health and compliance metrics
KEY KPIs
Access request turnaround
< 30 minutes
Failed login attempts rate
< 2% monthly
Orphaned accounts detected
Zero tolerance
Privileged account audit pass rate
> 98%
MFA adoption rate
100% of users

## Slide 11
Risk Mitigation & Contingency Planning
Organisational resistance to new authentication workflows
High
Mitigation: Early, transparent communication. Executive sponsorship visible from Day 1. Phased rollout with feedback channels open throughout.
System downtime during cutover weekend
High
Mitigation: Maintenance window scheduled off-peak. Rollback snapshots pre-tested. War room staffed 24/7 during cutover window.
Legacy system integration failures
Medium
Mitigation: Custom connectors tested in isolated environment before production. Parallel operation period maintained for 4 weeks post-cutover.
Data consistency failures across identity stores
Medium
Mitigation: Real-time sync validation scripts deployed. Automated alerts trigger on sync lag exceeding 60 seconds.

## Slide 12
Conclusion & Next Steps
PROGRAMME SUMMARY
This IAM Implementation Plan delivers a secure, scalable, and compliant identity framework across TechCorp's enterprise systems. The 7-month phased approach minimises operational disruption while achieving full zero-trust identity enforcement, regulatory compliance, and long-term operational efficiency gains.
IMMEDIATE NEXT STEPS
1. Secure executive sign-off and formal programme budget approval
2. Formally assign Phase 1 team leads and confirm resource availability
3. Schedule kick-off stakeholder workshop within the next 2 weeks
4. Issue RFP for IAM platform vendor evaluation (Okta vs. Microsoft Azure AD)
5. Establish programme governance structure and reporting cadence
TechCorp | IAM Implementation Plan | Confidential | Prepared by Prince Ndutimi